## list
Implementer | Main Activity | Sub Activity | Deliverables | Start Date | End Date | Expected Results
RFA | 1.1.1. Identify 100 sub-areas of intervention (400 ha each) for agroforestry dissemination over Eastern Province | 1.1.1.1. Cross-check and validation of restored priority areas for agroforestry interventions | Verified maps | 2026-01-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.1. Identify 100 sub-areas of intervention (400 ha each) for agroforestry dissemination over Eastern Province | 1.1.1.1. Cross-check and validation of restored priority areas for agroforestry interventions | Shapefiles in FMES | 2026-01-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.1. Identify 100 sub-areas of intervention (400 ha each) for agroforestry dissemination over Eastern Province | 1.1.1.1. Cross-check and validation of restored priority areas for agroforestry interventions | Validation Report | 2026-01-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.1: Organize, sensitize and train 100 farmer’s facilitors/promotors | Training manuals on Agroforestry techniques | 2026-04-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.1: Organize, sensitize and train 100 farmer’s facilitors/promotors | AF Training Progress Report | 2026-04-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.1: Organize, sensitize and train 100 farmer’s facilitors/promotors | List of training participants | 2026-04-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.1: Organize, sensitize and train 100 farmer’s facilitors/promotors | Signed MoUs between the project and FFS groups/Twigire Muhinzi | 2026-04-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.1: Organize, sensitize and train 100 farmer’s facilitors/promotors | Signed MoUs between FFS groups/Twigire Muhinzi and lead farmers | 2026-04-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.2: Identify and implement agroforestry systems and species | Guideline for the design of agroforestry systems available | 2026-01-01 | 2026-07-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.2: Identify and implement agroforestry systems and species | Training Report: Farmer promotors and facilitators trained. | 2026-01-01 | 2026-07-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.3: Established MoUs between local authorities and supported farmer groups to sustain agroforestry investment | Signed MoU available | 2026-02-01 | 2026-07-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.3: Established MoUs between local authorities and supported farmer groups to sustain agroforestry investment | Workshop report(+List of participants) | 2026-02-01 | 2026-07-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.4: Organize regular learning exchange meeting between farmer’s groups and reward champions | Learning exchange visit reports(+Attendance list) | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.4: Organize regular learning exchange meeting between farmer’s groups and reward champions | knowledge exchange workshop reports(+attendance list) | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.4: Organize regular learning exchange meeting between farmer’s groups and reward champions | List of champion farmers identified | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.4: Organize regular learning exchange meeting between farmer’s groups and reward champions | Field performance evaluation report of champion farmers | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | 1.1.2.4: Organize regular learning exchange meeting between farmer’s groups and reward champions | type of incentives provided to best champion farmers. | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | G1.1.2.1 Train women farmers and women groups climate resilient agricultural practices (e.g. agroforestry techniques) | Training report for women on climate resilient agricultural practices.(+list of participants) | 2026-05-01 | 2026-09-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | G1.1.2.1 Train women farmers and women groups climate resilient agricultural practices (e.g. agroforestry techniques) | Sensitization and awareness campaigns report | 2026-05-01 | 2026-09-30 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | G1.1.2.2 Train women in agricultural techniques that improve productivity; to produce agricultural products aimed at the market; and in post-harvest techniques, especially preservation, so that they can sell in times of scarcity (combined with G1.1.2.2) | Training report : Women, including FHH, trained in agricultural techniques (GAP)that improve productivity(+list of participants) | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.2: Train 160 farmers groups (including women groups) on agroforestry techniques and establish 160 MOUs with local authorities | G1.1.2.2 Train women in agricultural techniques that improve productivity; to produce agricultural products aimed at the market; and in post-harvest techniques, especially preservation, so that they can sell in times of scarcity (combined with G1.1.2.2) | Sensitization and awareness campaigns report | 2026-05-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.3. Establish and sustain one agroforestry/fruit trees nursery in each of the 100 sub-areas of intervention | 1.1.3.1. Supply of nursery equipment to farmer groups for seedlings production including reinnovation of established 100 tree nurseries | Supply report for nursery equipments to 70 Farmer groups tree nurseries | 2026-01-01 | 2026-01-31 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.3. Establish and sustain one agroforestry/fruit trees nursery in each of the 100 sub-areas of intervention | 1.1.3.2.a. Seeds and tree reproductive materials collection and distribution to farmer groups | Lists of tree seeds collected and distributed to farmer group tree nurseries | 2026-02-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.3. Establish and sustain one agroforestry/fruit trees nursery in each of the 100 sub-areas of intervention | 1.1.3.2.a. Seeds and tree reproductive materials collection and distribution to farmer groups | Supply / Field report | 2026-02-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.3. Establish and sustain one agroforestry/fruit trees nursery in each of the 100 sub-areas of intervention | 1.1.3.2.b Train community groups in production and maintenance of fruit trees under community approach activities in 7 Districts of Eastern Province | Training report: production and maintenance of fruit trees under community approach | 2026-04-01 | 2026-09-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.3. Establish and sustain one agroforestry/fruit trees nursery in each of the 100 sub-areas of intervention | 1.1.3.2.c. Production of tree seedlings by supported nursery groups (40% for beating up of landscape planted in 2025) | Seedlings acquisition report | 2026-04-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.3. Establish and sustain one agroforestry/fruit trees nursery in each of the 100 sub-areas of intervention | 1.1.3.2.d. Trees beating-up and maintenance of Agroforestry landscapes planted in 2025 | Plantation(beating-up) and maintenance report | 2026-07-01 | 2026-01-31 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.4. Provide technical assistance to farmers in planting agroforestry/fruit trees and in implementation of agroforestry technologies in their owned parcels | 1.1.4.1. Organize and conduct the study tours for peer learning on trees planting and implementation of agroforestry technologies | Study tours report for 100 team leaders and 7 DFMOs(+Attendance list) | 2026-04-01 | 2026-09-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.4. Provide technical assistance to farmers in planting agroforestry/fruit trees and in implementation of agroforestry technologies in their owned parcels | 1.1.4.2. Project visibility (sign posts for 30 landscapes) for Agroforestry landscape restoration | Sign posts for 30 AF landscapes installation report | 2026-01-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.1.4. Provide technical assistance to farmers in planting agroforestry/fruit trees and in implementation of agroforestry technologies in their owned parcels | 1.1.4.3.Support farmers to acquire the rain water harvesting equipment | rain water harvesting installation report | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.5: Establish and sustain 1 demonstration plot of 1-2 ha in each of the 100 sub-areas | 1.1.5.2: Establish framing contract between selected FFS groups and local authorities for maintaining the demonstration plot | 30 MoUs Signed | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.5: Establish and sustain 1 demonstration plot of 1-2 ha in each of the 100 sub-areas | 1.1.5.2: Establish framing contract between selected FFS groups and local authorities for maintaining the demonstration plot | Workshop report+'List of participants | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.5: Establish and sustain 1 demonstration plot of 1-2 ha in each of the 100 sub-areas | 1.1.5.3: Established demonstration plots, train responsible farmer leaders and ensure maintenance | Training materials available on best agronomic practices | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.5: Establish and sustain 1 demonstration plot of 1-2 ha in each of the 100 sub-areas | 1.1.5.3: Established demonstration plots, train responsible farmer leaders and ensure maintenance | Technical reports: 100 demo plots maintained/upgraded with best agronomic practices | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.5: Establish and sustain 1 demonstration plot of 1-2 ha in each of the 100 sub-areas | 1.1.5.3: Established demonstration plots, train responsible farmer leaders and ensure maintenance | Training reports: 300 responsible farmers+ List of trained responsible farmers | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
ICRAF | 1.1.5: Establish and sustain 1 demonstration plot of 1-2 ha in each of the 100 sub-areas | 1.1.5.3: Established demonstration plots, train responsible farmer leaders and ensure maintenance | Outreach/farmer field days reports | 2026-01-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
IUCN | 1.1.6. Monitoring, control and evaluation of supported agroforestry areas | 1.1.6.1. Agroforestry area will be mapped and registered in the agroforestry database which is embedded in the RFA DFMP database. GPS tablet and specifically designed user friendly agroforestry functionalities will allow direct mapping in the field, of: 1) every consolidated block of 5-10 ha, 2) the registration of list of owner and of names of farmer leaders/FFS facilitators/FPs, 3) the registration for each block of the number of existing and /or planted trees per species, 4) the archiving and consultation of the signed MoU, 5) etc. Linked to 1.1.1: i.e. mapping and registering of the agroforestry intervention areas in the agroforestry database - embedded in the RFA DFMP database -; hence will start as soon as 1.1.1 will start/is ongoing. Question: "specifically designed user friendly agroforestry functionalities" is this already available/needs to be developed? | District Forest Management Plan (DFMP) database. | 2026-01-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
IUCN | 1.1.6. Monitoring, control and evaluation of supported agroforestry areas | 1.1.6.1. Agroforestry area will be mapped and registered in the agroforestry database which is embedded in the RFA DFMP database. GPS tablet and specifically designed user friendly agroforestry functionalities will allow direct mapping in the field, of: 1) every consolidated block of 5-10 ha, 2) the registration of list of owner and of names of farmer leaders/FFS facilitators/FPs, 3) the registration for each block of the number of existing and /or planted trees per species, 4) the archiving and consultation of the signed MoU, 5) etc. Linked to 1.1.1: i.e. mapping and registering of the agroforestry intervention areas in the agroforestry database - embedded in the RFA DFMP database -; hence will start as soon as 1.1.1 will start/is ongoing. Question: "specifically designed user friendly agroforestry functionalities" is this already available/needs to be developed? | 2 M&E and quality control missions reports | 2026-01-01 | 2026-06-30 | Output 1.1: Diversified agroforestry packages scaled-up
IUCN | 1.1.6. Monitoring, control and evaluation of supported agroforestry areas | 1.1.6.1.b Training of field data collectors + provision of data collection materials including tablets | training reports+list of enumerators trained | 2026-02-01 | 2026-08-31 | Output 1.1: Diversified agroforestry packages scaled-up
IUCN | 1.1.6. Monitoring, control and evaluation of supported agroforestry areas | 1.1.6.1.c Quality control of agroforestry area restored, their mapping and registration in the RFA FMES and DFMP | 100 sub areas M&E reports. | 2026-03-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
IUCN | 1.1.6. Monitoring, control and evaluation of supported agroforestry areas | 1.1.6.1.c Quality control of agroforestry area restored, their mapping and registration in the RFA FMES and DFMP | AF sites Maps | 2026-03-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
IUCN | 1.1.6. Monitoring, control and evaluation of supported agroforestry areas | 1.1.6.1.c Quality control of agroforestry area restored, their mapping and registration in the RFA FMES and DFMP | RFA FMES & DFMP Report/Database | 2026-03-01 | 2026-12-31 | Output 1.1: Diversified agroforestry packages scaled-up
RFA | 1.2.1. Restore 700 ha of very degraded State owned tree plantations and provide technical assistance for their sustainable management | 1.2.1.5.a Supply the nursery equipment for the restoration of 569ha of state forests which are the most degraded and/or located in sloppy areas most exposed to soil degradation | nursery equipment supply report | 2026-01-01 | 2026-06-30 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.1. Restore 700 ha of very degraded State owned tree plantations and provide technical assistance for their sustainable management | 1.2.1.5.b Seedlings production for restoration of 569 ha of state forests which are the most degraded and/or located in sloppy areas most exposed to soil degradation | Seedlings production&job creation report | 2026-04-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.1. Restore 700 ha of very degraded State owned tree plantations and provide technical assistance for their sustainable management | 1.2.1.5.c Remuneration of firm to restore 569 ha of state forests which are the most degraded and/or located in sloppy areas most exposed to soil degradation | Restoration & job creation report | 2026-04-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.1. Restore 700 ha of very degraded State owned tree plantations and provide technical assistance for their sustainable management | 1.2.1.5.d Monitoring of the restoration of 569 Ha | Field missions report | 2026-02-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.2. Restore, in collaboration with RFA and Districts, an area of 700 ha of very degraded State owned tree plantations and in long-term concession of 10,000 ha of State FMUs to private investors | 1.2.2.1. State forest stand ownership conflict demarcation (all districts) | Conflict resolution report | 2026-01-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.2. Restore, in collaboration with RFA and Districts, an area of 700 ha of very degraded State owned tree plantations and in long-term concession of 10,000 ha of State FMUs to private investors | 1.2.2.2. Supply the nursery equipment for the restoration of 376.2 ha of state forests which are the most degraded and/or located in sloppy areas most exposed to soil degradation | nursery equipment supply report | 2026-02-01 | 2026-09-01 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.2. Restore, in collaboration with RFA and Districts, an area of 700 ha of very degraded State owned tree plantations and in long-term concession of 10,000 ha of State FMUs to private investors | 1.2.2.3. Seedlings production for restoration of 376.2 ha of state forests which are the most degraded and/or located in sloppy areas most exposed to soil degradation | Seedlings production & jobs creation report | 2026-04-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.2. Restore, in collaboration with RFA and Districts, an area of 700 ha of very degraded State owned tree plantations and in long-term concession of 10,000 ha of State FMUs to private investors | 1.2.2.4. Remuneration of firm to restore 376.2 ha of state forests which are the most degraded and/or located in sloppy areas most exposed to soil degradation | Restoration & jobs creation report | 2026-05-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.2. Restore, in collaboration with RFA and Districts, an area of 700 ha of very degraded State owned tree plantations and in long-term concession of 10,000 ha of State FMUs to private investors | 1.2.2.5. Monitoring of the restoration of 274 ha | Monitoring restoration activities report | 2026-01-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.1. Selection of targeted landscapes to be restored in each District | Reports of 65 sites and final shapefiles | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.2. Identify blocks of private forest lands to be restored | final shapefiles of restored PFMUs pushed to FMES database | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.3. Build capacity of local stakeholders on new private FMU approach and methods, including feild visit of existing PFMU in Eastern Rwanda | Activity report : capacity building of local stakeholders on new private FMU approach. | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.4.a. Establish MoUs for each small-holder group (including women and youth) to engage in private FMUs management | MoU signed: women and youth engagement in private FMUs management. | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.4.b. Support smallholders in private FMU cooperatives establishment. | Final RCA registration certificates for PFMU cooperatives | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.5. Restore 4000 ha of the targeted 6.545 ha of smallholder forests and support their right implementation | Activity report: 1500 Ha of PFMU mentained (beating up, maintenance and final reception). | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.6. Design and approved SFMPs of private FMUs, and support their right implementation (Y2: Support the design uo to approval of SFMPs of PFMUs) | Activity report: 65 SFMPs completed for PFMUs planted in Season 2023-2025. | 2026-01-01 | 2026-10-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
IUCN | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | G1.2.1 Establish an MoU for female headed groups to engage in private FMUs management according to approved SFMPs and support them | Training reports: capacity building session on climate change resilience and gender | 2026-04-01 | 2026-06-30 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.7. Field validation of shapefiles provided by IUCN of 2,545 ha of the most degraded PFMUs to be restored by RFA | Site checking report: 2545 ha Boundary, conflict checking and site validation | 2026-01-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.8.a. Organize the forest owners into farmer groups; to carryout the restoration of PFMUs | 50 Farmer groups establishmnet report | 2026-01-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
RFA | 1.2.3. Restoration, in collaboration with smallholders, the area of 6,545 ha of very degraded private tree plantations and their sustainable management under private FMUs | 1.2.3.8.b. Restore and maintain 2,545 ha of the most degraded PFMUs | 2545 ha of the PFMUs restoration report | 2026-01-01 | 2026-12-31 | Output 1.2: Woodlot and tree plantations are rehabilitated and sustainably managed for productive and ecological services
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.2. Identification of existing tree and forage species composition in grazing land: Process manuscripts for publication in peer reviewed journals | 2 scientific publications. | 2026-01-01 | 2026-06-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.4. Estimation of pasture productivity, cost benefit analysis in current climate trends and prediction of the change after intervention and in future climate trends | Study Report: pasture productivity& cost benefit analysis | 2026-04-01 | 2026-06-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.5. Conduct carrying capacity study of the grazing land: a. Farm selection for carrying capacity study b. Paddocking of grazing land for carrying capacity study | At least 6 farms selected for carrying capacity study(4.6 ha paddocked for cc study) | 2026-09-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.5. Conduct carrying capacity study of the grazing land: a. Farm selection for carrying capacity study b. Paddocking of grazing land for carrying capacity study | technical report | 2026-10-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.5. Conduct carrying capacity study of the grazing land: a. Farm selection for carrying capacity study b. Paddocking of grazing land for carrying capacity study | Database on carrying capacity | 2026-11-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.6. Design silvo-pastoral plan, integrated with the District Land Use Plan | Consultancy contract | 2026-01-01 | 2026-01-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.6. Design silvo-pastoral plan, integrated with the District Land Use Plan | Consultancy Report: draft Silvopastoral plans developed | 2026-02-01 | 2026-03-10 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.6. Design silvo-pastoral plan, integrated with the District Land Use Plan | Validation workshop Report of silvopastoral plans | 2026-03-15 | 2026-03-25 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.1: Characterize the climate vulnerabilities of the existing pasture lands | 1.3.1.6. Design silvo-pastoral plan, integrated with the District Land Use Plan | 6 Silvopastoral plan developed | 2026-03-25 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.2: Select fodder trees, shrubs, grasses, and herbaceous legumes with high drought resilience potential to increase the climate adaptive capacity of the pasture lands | 1.3.2.3. Tree seeds and forage species acquisition | Purchase orders and delivery note | 2026-01-01 | 2026-01-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.2: Select fodder trees, shrubs, grasses, and herbaceous legumes with high drought resilience potential to increase the climate adaptive capacity of the pasture lands | 1.3.2.3. Tree seeds and forage species acquisition | 500,000 agroforestry seedlings produced | 2026-02-01 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.2: Select fodder trees, shrubs, grasses, and herbaceous legumes with high drought resilience potential to increase the climate adaptive capacity of the pasture lands | 1.3.2.4. Training on tree and forage nurseries set-up, management, planting material distribution and enterprise development, ensure women and female headed HH benefits | Updated training manuals available | 2026-03-01 | 2026-07-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.2: Select fodder trees, shrubs, grasses, and herbaceous legumes with high drought resilience potential to increase the climate adaptive capacity of the pasture lands | 1.3.2.4. Training on tree and forage nurseries set-up, management, planting material distribution and enterprise development, ensure women and female headed HH benefits | Training report(+Attendance lists) | 2026-03-01 | 2026-07-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.2: Select fodder trees, shrubs, grasses, and herbaceous legumes with high drought resilience potential to increase the climate adaptive capacity of the pasture lands | G1.3.2 Identify women as farmer promotors on improved fodder technologies and provide/disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | List of women farmer promotors available | 2026-01-01 | 2026-06-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.2: Select fodder trees, shrubs, grasses, and herbaceous legumes with high drought resilience potential to increase the climate adaptive capacity of the pasture lands | G1.3.3 Enhance the capacity of women lead farmers (train the trainers) from local communities on management grazing lands for climate resilient pasture productivity. | report on women who trained on management of grazing land | 2026-06-30 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.1. Stakeholders engagement: Dialogue/ negotiation, selection, organization and awareness creation for farmer promotors on improved fodder technologies to improve grazing land and build resilience of degraded lands | 4 stakeholder engagement meeting reports (+Attendance lists) | 2026-01-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.1. Stakeholders engagement: Dialogue/ negotiation, selection, organization and awareness creation for farmer promotors on improved fodder technologies to improve grazing land and build resilience of degraded lands | 4 awareness raising compaigns targetting women farmer promoters | 2026-04-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.2. Maintenance of pilot demonstration as model pasture lands including different grasses and fodder legumes | 40 pilot forage demo plots | 2026-02-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.2. Maintenance of pilot demonstration as model pasture lands including different grasses and fodder legumes | Technical reports on 30 ha of model pasturelands | 2026-02-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.3. Support farmers in planting/maintaining agroforestry fodder trees, timber, fruit trees and grasses in farmers pastures, in contour or scattered in pasture | Maintaining 5,000 ha of restored grazing land( 600,000 tree seedlings planted) | 2026-03-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.4. Establish and maintain farms demarcation and paddocking using agroforestry, timber and fodder trees | Paddock grazing management systems established on 10,000 Ha | 2026-08-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.3: Purchase and disseminate agroforestry fodder trees, improved grasses and herbaceous legumes to improve grazing land and build resilience of degraded lands | 1.3.3.4. Establish and maintain farms demarcation and paddocking using agroforestry, timber and fodder trees | Technical reports | 2026-09-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.1. Training 30 leader farmers (ToTs) including women farmers, on management of trees (harvesting tree leaves for feeding the cows, pruning, thinning) for improving milk and meat productivity: a. Development of training manuals b. Practical training and c. Farmer exchange field visit | 1 training module updated | 2026-02-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.1. Training 30 leader farmers (ToTs) including women farmers, on management of trees (harvesting tree leaves for feeding the cows, pruning, thinning) for improving milk and meat productivity: a. Development of training manuals b. Practical training and c. Farmer exchange field visit | Training reports(+ Attendance sheets) | 2026-02-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.1. Training 30 leader farmers (ToTs) including women farmers, on management of trees (harvesting tree leaves for feeding the cows, pruning, thinning) for improving milk and meat productivity: a. Development of training manuals b. Practical training and c. Farmer exchange field visit | 6 farmer exchange visits + List of farmer participants | 2026-02-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.2. Training 30 farmers on mixing fodder tree leaves and grasses for improved animal nutrition | 1 training module updated | 2026-02-01 | 2026-05-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.2. Training 30 farmers on mixing fodder tree leaves and grasses for improved animal nutrition | Training reports(+ Attendance sheets) | 2026-01-01 | 2026-06-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.3. Training 30 farmers on manure composting for enhanced rangeland productivity | Training reports(+Attendance sheets) | 01/08/0206 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.4. Training on harvesting time of grasses for optimizing grasses use, reduce fodder deficit during the dry season and grazing management for restoring degraded lands and fodder budgeting (grazing rotation) | Training reports(+Attendance sheets) | 2026-02-01 | 2026-10-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.4: Organize two Training of Trainers (ToT) sessions per year for 30 lead farmers on management grazing lands for climate resilient pasture productivity | 1.3.4.4. Training on harvesting time of grasses for optimizing grasses use, reduce fodder deficit during the dry season and grazing management for restoring degraded lands and fodder budgeting (grazing rotation) | 2 updated training modules | 2026-02-01 | 2026-10-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.5: Assess water availability and rainwater potential harvesting in 60 pastures and purchase 60 water tanks of 5000 m3 to reduce drought stress for the livestock | 1.3.5.1. Mapping water availability in pastures of the Eastern Province (completed ) | Validation warkshop report | 2026-01-01 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.5: Assess water availability and rainwater potential harvesting in 60 pastures and purchase 60 water tanks of 5000 m3 to reduce drought stress for the livestock | 1.3.5.1. Mapping water availability in pastures of the Eastern Province (completed ) | Final water availability mapping report | 2026-01-01 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.5: Assess water availability and rainwater potential harvesting in 60 pastures and purchase 60 water tanks of 5000 m3 to reduce drought stress for the livestock | 1.3.5.4. Organize and train 15 livestock communities for water Infrastructure management (rainwater harvesting and water use), (Note: including building capacity of women within livestock communities who benefit from water management) | 8 livestock communities trained (+Attendance sheets) | 2026-04-01 | 2026-07-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.5: Assess water availability and rainwater potential harvesting in 60 pastures and purchase 60 water tanks of 5000 m3 to reduce drought stress for the livestock | G1.3.5.4 Building capacity of women within livestock communities on water infrastructure management (water tanks, rainwater harvesting and water use) | Training report on water infrastructure management(+Attendance list) | 2026-06-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.1. Meeting with livestock communities | landscape meeting reports(+ Attendance sheets) | 2026-01-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.2. Identification of knowledge gaps in management of rangelands for government extension service and farmer leaders | Field consultation/meeting reports | 2026-02-01 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.2. Identification of knowledge gaps in management of rangelands for government extension service and farmer leaders | Report on assessment of knowledge gaps available | 2026-02-01 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.2. Identification of knowledge gaps in management of rangelands for government extension service and farmer leaders | Focus group discussion report | 2026-02-01 | 2026-03-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.3. Awareness raising for 7 local authorities and 7 church leaders for mobilizing livestock communities | Field reports of awareness raising sessions(+List of participants) | 2026-02-01 | 2026-09-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.4. Training 7 government extension (men and women) staff and 30 farmer leaders (men and women) on fodder production and pasture management (grasses, water and trees) | Training reports(+Attendance lists) | 2026-02-01 | 2026-09-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | G1.3.5 Build capacity of women lead farmers, women government extension staff, women church leaders and women local authorities in charge of development in 7 districts (activity 1.3.6) | Report on capacity building of women lead farmers, women government extension staff, women church leaders and women local authorities. | 2026-04-01 | 2026-06-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.5. Develop extension materials (Training manuals, posters and leaflets) and involve media for information dissemination through radio, TV and newsletters | Available extension material in English and Kinyarwanda | 2026-05-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.5. Develop extension materials (Training manuals, posters and leaflets) and involve media for information dissemination through radio, TV and newsletters | Radio and TV spots developed and disseminated. | 2026-05-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.5. Develop extension materials (Training manuals, posters and leaflets) and involve media for information dissemination through radio, TV and newsletters | Newsletters , posters and policy briefs available. | 2026-05-01 | 2026-08-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | G1.3.6 Promote awareness campaigns on women’s rights (including GBV) that target women, men, including local leaders and source of influence to promote the enforcement of such rights. (link with activity 1.3.6.5) | 6 awareness compaigns organized | 2026-06-01 | 2026-10-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | G1.3.6 Promote awareness campaigns on women’s rights (including GBV) that target women, men, including local leaders and source of influence to promote the enforcement of such rights. (link with activity 1.3.6.5) | 3 information leaflets produced and disseminated | 2026-06-01 | 2026-10-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.6 Organise regular learning exchange visits between livestock farmer’s groups and reward champion farmers | 3 learning exchange visits (+Attendance sheets ) | 2026-07-01 | 2026-09-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.6 Organise regular learning exchange visits between livestock farmer’s groups and reward champion farmers | At least 12 livestock champion farmers identified and rewarded | 2026-07-01 | 2026-09-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.6: Conduct twice per year capacity building workshops for 30 lead farmers, 7 government extension staff, 7 church leaders and 7 local authorities in charge of development in 7 districts | 1.3.6.6 Organise regular learning exchange visits between livestock farmer’s groups and reward champion farmers | 450 livestock farmers trained by model farmers | 2026-07-01 | 2026-09-30 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
IUCN | 1.3.7: Monitoring and evaluation of silvopastoral activities | 1.3.7.1. This activity aims at ensuring that silvopastoral activities are effectively and efficiently implemented, and technical support as well as extension services are provided to beneficiaries in the project. The regular monitoring will also enable tracking impact at farm level both biophysical and social economic. 1.3.7.1. Conduct quarterly monitoring visits to project sites | D1.3.7.1: Quarterly monitoring reports | 2026-01-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
ICRAF | 1.3.7: Monitoring and evaluation of silvopastoral activities | 1.3.7.1. This activity aims at ensuring that silvopastoral activities are effectively and efficiently implemented, and technical support as well as extension services are provided to beneficiaries in the project. The regular monitoring will also enable tracking impact at farm level both biophysical and social economic. 1.3.7.1. Conduct quarterly monitoring visits to project sites | Biophysical maps indicating area where interventions resulted net positive change in water and carbon | 2026-01-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
IUCN | 1.3.7: Monitoring and evaluation of silvopastoral activities | 1.3.7.2. Carry out data collection from households to enable impact tracking | D1.3.7.2: Impact tracking dashboard | 2026-07-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
IUCN | 1.3.7: Monitoring and evaluation of silvopastoral activities | 1.3.7.3. Using baseline data, collect geographical information coordinates to produce updated biophysical maps for landscapes | D1.3.7.3: Maps indicating area already where intervention took place with any net positive change in water and carbon. | 2026-07-01 | 2026-12-31 | Output 1.3: Scale-up climate resilient silvopastoral packages to restore degraded rangelands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.1. Identified priority roadsides to be protected reassessed at time of inception for changes since project submission / Assess and identify priority roadsides to be protected | Identification and mapping report | 2026-01-01 | 2026-07-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.1.a Nursery Equipment to produce tree seedlings to restore roadsides 231.8km roadsides | Supply report of Nursery equipment supply for 231.8 km roadsides protection | 2026-02-01 | 2026-07-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.2. Establish roadside CVCs and sign participatory management MoUs. | Signed MoUs | 2026-02-01 | 2026-09-30 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.3.a. Seedlings production of high quality seedlings and transport to the planting site (For 231.8km plus 40% of beating up on 227.7km restored roadsides by 2025) | Seedlings production report | 2026-05-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.3.b. Conduct participatory tree/shrub planting campaign; Remuneration for quality tree seedlings production, tree planting work as maintenance until the handover of planted trees | Planting and maintenance report | 2026-05-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.3.e. Provide technical assistance to RFA in design of required regulation for management of the specific cases of roadside plantation and river/lake shore plantation integrating climate resilience | Roadsides and wetlands plantation guidelines | 2026-05-01 | 2026-09-30 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.1 Restore 700 ha of lake/river shorelines and 700 km of roadside through tree/shrub planting and participatory management | 1.4.1.3.f. Grafted fruit seedlings production and supply (10% of the total seedlings to be planted on roads and lakesides: seedlings production and transport to the planting site) | Report of grafted fruit trees produced and supplied | 2026-02-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.2 Restore and protect 400 ha of the Akagera buffer zone through tree/shrub planting and implementation of a participatory silvopastoral plan | 1.4.2.1.a. Monitoring of beating up activities | At least 10 monitoring missions &reports | 2026-01-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.2 Restore and protect 400 ha of the Akagera buffer zone through tree/shrub planting and implementation of a participatory silvopastoral plan | 1.4.2.1.b. Final evaluation of the restored bufferzone | 1 Evaluation mission & report | 2026-01-01 | 2026-07-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.3 Provide technical support to 3 local nurseries in production of selected climate resilient multipurpose trees/shrub seedlings | 1.4.3.1. Support local nurseries in production of selected climate multipose fruit seedlings | Field visits reports of tree nurseries technically supported | 2026-02-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.3 Provide technical support to 3 local nurseries in production of selected climate resilient multipurpose trees/shrub seedlings | 1.4.3.1. Support local nurseries in production of selected climate multipose fruit seedlings | Delivery notes of assets/equipmentand/Material reception registration | 2026-02-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.3 Provide technical support to 3 local nurseries in production of selected climate resilient multipurpose trees/shrub seedlings | 1.4.3.1. Support local nurseries in production of selected climate multipose fruit seedlings | Training reports on production of selected climate resilient multipurpose trees/shrub seedlings | 2026-02-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.1 Conduct a ToT for the district and sector staffs on roadsides and wetlands restoration and protection | Training report on roadsides and wetlands restoration and protection (+List of participants) | 2026-01-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.1.a. Integrate new specific functionalities for M&E of these protected areas in the DFMP database (see output 3.2) Upgrading FMES for good functionality (features and equipment) | workshop report(+Participants list) | 2026-01-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.1.a. Integrate new specific functionalities for M&E of these protected areas in the DFMP database (see output 3.2) Upgrading FMES for good functionality (features and equipment) | 102 District staff supported to collect forest data using GPS tablets for the FMES mobile application | 2026-01-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.2.b. Integrate new specific functionalities for M&E of these protected areas in the DFMP database (see output 3.2) Conduct Forest Monitoring and Evaluation System (FMES) training for RFA and District staff and other implementing Partners staffs | System updated | 2026-06-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.2.b. Integrate new specific functionalities for M&E of these protected areas in the DFMP database (see output 3.2) Conduct Forest Monitoring and Evaluation System (FMES) training for RFA and District staff and other implementing Partners staffs | Training report: FMES training for RFA and District staff and other implementing Partners | 2026-06-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.2.d) Provide financial support to the seven districts to perform regural monitoring and evaluation of restored areas | Report of 7 districts finacially supported | 2026-01-01 | 2026-12-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.3.a. Contribution overall project audit (cost sharing with other IPs) and internal audit | 2025 Audit report | 01/04/1016 | 2026-09-30 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.3.b. Organize annual M&E field mission for the restored areas under special protection Support District staff for monitoring of restored landscapes | 2 M&E field missions report | 01/06/1016 | 2026-10-31 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
RFA | 1.4.4 Provide technical assistance to the seven districts to perform monitoring and evaluation of restored areas under protection integrating climate resilience Monitoring &Evaluation and Audit | 1.4.4.3.C. Mainstreaming gender in all project activities | Gender mainstreaming workshop report | 01/05/1016 | 2026-09-30 | Output 1.4: Protective restoration measures are scaled up to climate-proof fragile, ecologically sensitive and erosion prone lands
IUCN | 1.5.1: Conduct a large scale and intensive awareness campaign across the Eastern Province on ICS and cooking fuel solutions and opportunities | 1.5.1.1. Select the ICS models adapted to HHs needs and to be promoted (including testing, as baseline) | Knowledge Product for the selected model | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.1: Conduct a large scale and intensive awareness campaign across the Eastern Province on ICS and cooking fuel solutions and opportunities | 1.5.1.2. Develop the communication strategy, tools and messages adapted to rural HHs. | Link to media stories | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.1: Conduct a large scale and intensive awareness campaign across the Eastern Province on ICS and cooking fuel solutions and opportunities | 1.5.1.2. Develop the communication strategy, tools and messages adapted to rural HHs. | concept note on media tours organised | 2026-03-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.1: Conduct a large scale and intensive awareness campaign across the Eastern Province on ICS and cooking fuel solutions and opportunities | 1.5.1.2. Develop the communication strategy, tools and messages adapted to rural HHs. | List of awareness materials produced. | 2026-03-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.1: Conduct a large scale and intensive awareness campaign across the Eastern Province on ICS and cooking fuel solutions and opportunities | 1.5.1.3. Conduct awareness campaign in rural area of the EP. | 100 awarness campaings conducted targetting 80,000 beneficiaries | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.2: Support access to ICSs for over 100,000 rural Households of EP | 1.5.2.1. a Develop and validate subsidy scheme and rules with ICS sector actors | Report or MININFRA Approval Documentation | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.2: Support access to ICSs for over 100,000 rural Households of EP | 1.5.2.2. Subsidize dissemination of ICSs for poorest HHs. Ensure female-headed HHs access to ICS | 80,000 ICS distribution report | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.2: Support access to ICSs for over 100,000 rural Households of EP | 1.5.2.3. Support private sector in biomas fuel / ICS business development. | D1.5.2.2: Business models for private sector (report and guidance) | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.3: Establish “Clean Cooking fuel and technology” hubs in 14 main local markets of TREPA intervention areas | 1.5.3.1. Develop “Clean Cooking material and technology” hubs business model and internal rules: Y2 - Faesibility study with suppliers) | Awareness campaign report | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.3: Establish “Clean Cooking fuel and technology” hubs in 14 main local markets of TREPA intervention areas | 1.5.3.2.a Identify most strategic market location for hub establishment. | List and Maps of selected most strategic market location | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.3: Establish “Clean Cooking fuel and technology” hubs in 14 main local markets of TREPA intervention areas | 1.5.3.3 b. Design the clean cooking hub architectural plan | Hub architectural drawings | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.3: Establish “Clean Cooking fuel and technology” hubs in 14 main local markets of TREPA intervention areas | 1.5.3.4. Support the establishement of ICS hub (pilot or full scale) | ICS hub establishement Reports | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.3: Establish “Clean Cooking fuel and technology” hubs in 14 main local markets of TREPA intervention areas | 1.5.3.5. Train hub staff and establish accounting and financial procedures | Training report+attendance list | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.4. Provide feedback into enabling environment activities supporting the shift from traditional cooking to clean ICS and fuels | 1.5.4.1 Develop standard and minimum performance requirements for ICS that will be disseminated through “Cooking | Ministreial guidelines/instructions or other regulation/policy text D1.5.4.1.: Standard and minimum performnce Requirements Report | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
IUCN | 1.5.4. Provide feedback into enabling environment activities supporting the shift from traditional cooking to clean ICS and fuels | 1.5.4.2 Provide inputs into policies and taxation systems incentivizing adoption and use of high-efficiency stoves | Ministreial guidelines/instructions or other regulation/policy text D1.5.4.2.: Technical notes/reports for policies | 2026-01-01 | 2026-12-31 | Output 1.5: Clean and efficient cooking energy technologies promoted through support to private sector and communities to transition/reduce biomass fuel consumption
ICRAF | 2.2.1: Tree crop value chain development | 2.2.1.1 establishment of seed enterprises | Technical report of seed enterprise establishement | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.1: Tree crop value chain development | 2.2.1.1 establishment of seed enterprises | Business plans available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.1: Tree crop value chain development | 2.2.1.2 establishment of nursery enterprises | district-level tree nursery enterprises established | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.1: Tree crop value chain development | 2.2.1.2 establishment of nursery enterprises | Business plans available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.1: Tree crop value chain development | 2.2.1.3 establishment of contractual wood farming | Wood farm contracts available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.1: Tree crop value chain development | 2.2.1.3 establishment of contractual wood farming | Business plans available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.1. Strengthening beekeeping cooperatives | 9 honey/wax storage stations and associated processing facilities | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.1. Strengthening beekeeping cooperatives | Training Report: coop members trained on honey production and value-adding+ List of trained beekeepers | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.1. Strengthening beekeeping cooperatives | Training materials available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.1. Strengthening beekeeping cooperatives | Bussiness plans available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.2. Improving tree-based bee forage | 85 ha of land with tree-based bee forage | 2026-03-01 | 2026-11-30 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.2. Improving tree-based bee forage | Field visit reports & List of cooperatives having established bee forage trees | 2026-03-01 | 2026-11-30 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.3. Introduction and distribution of modern beehives | Purchase order and delivery note of improved beehives | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.3. Introduction and distribution of modern beehives | Acknowledgement receipts of beehives by cooperatives | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.4. Akagera brand' establishment for landscape labelled honey and wax products | 5 beekeiping coops with Akagera brand labelled honey and wax products | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.2: Bee product value chain development | 2.2.2.4. Akagera brand' establishment for landscape labelled honey and wax products | S-Mark certificates available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.1. Establishment of livestock feed enterprises and storage areas | 1 livestock feed enterprise and storage area established | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.1. Establishment of livestock feed enterprises and storage areas | Training Reporton fodder enterprise development(+List of participants) | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.1. Establishment of livestock feed enterprises and storage areas | Training materials available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.1. Establishment of livestock feed enterprises and storage areas | Bussiness plans available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.2. Establishment of restoration enterprises | 2 district-level restoration enterprises operated by youth | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.2. Establishment of restoration enterprises | Training Report: youth and women provided with enterprise development assistance& List of participants | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.2. Establishment of restoration enterprises | Training materials available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.2. Establishment of restoration enterprises | Bussiness plans available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.3: Fodder value chain development | 2.2.3.3. Proper management of existing cooling and storage stations | Training report on proper management of milk cooling and storage stations+' List of trained members of MCC | 2026-02-01 | 2026-06-30 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.4: Building local capacity and knowledge for climate resilience in value chains | 2.2.4.1 Development of training modules on climate-resilient agribusiness | Training modules on climate-resilient agribusiness available | 2026-01-01 | 2026-03-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.4: Building local capacity and knowledge for climate resilience in value chains | 2.2.4.2 Delivery of training modules on climate-resilient agribusiness | 100 policy makers and service providers trained | 2026-04-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.5: Establish/Rehabilitate seven rural resource centers and market infrastructures for value chains for climate resilient agricultural and tree products | 2.2.5.1 Establish rural resource centers that serve as the go to centres for training and learning processes for farmers and local communities. | 3 RRC rehabilited and consolidated in terms of nursery infrastructure and business plans | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.6:Trade fairs and business roundtables connecting farmers with other value chains actors for marketing products based on climate-resilient land use | 2.2.6.1. Organize annual business roundtable on fodder value chain | Report of the business roundtable on on fodder value chain organized(+List of participants) | 2026-05-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
IUCN | 2.2.6:Trade fairs and business roundtables connecting farmers with other value chains actors for marketing products based on climate-resilient land use | 2.2.6.2. Organize trade fairs in Year 2, 3, 4 and 5: a. participate in the assessment b)Support the organization of trade fairs | Technical report D2.2.6.1: Trade fairs focusing on portfolio of targeted value chains | 2026-06-01 | 2026-08-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
IUCN | 2.2.7: ICT supported climate risk, market information and knowledge products for climate resilience in value chains | 2.2.7.1. Compile and disseminate market information: a. develop ToRs, b. recruit consultant to compile information, c. share compiled information | Number of market and climate riks information packages delivered for relevant value chains | 2026-08-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.7: ICT supported climate risk, market information and knowledge products for climate resilience in value chains | 2.2.7.2 Establish farmer-to-farmer communication | 1 climate information package | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.7: ICT supported climate risk, market information and knowledge products for climate resilience in value chains | 2.2.7.2 Establish farmer-to-farmer communication | 100 trained communication champions& attendance list | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
ICRAF | 2.2.7: ICT supported climate risk, market information and knowledge products for climate resilience in value chains | 2.2.7.3 Produce user friendly knowledge products | Knowledge products for climate-resilient agribusiness available | 2026-01-01 | 2026-12-31 | Output 2.2 Enhanced climate resilience of agricultural value chains and commodities
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | 7 refresher training conducted to the facilitators from the community (+Attendence sheets) | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | 150 FFPOs savings groups and 25 saving groups from PFMUs 225 from the community(+Group registration lists) | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | 1000 communication and learning materials produced | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | 100 monitored people coached+attendance sheets | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | 4 QRMs organised with SGAs and CMs | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | 1 SG Model validated | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | A clear Database of 10,000 new beneficiaries is available | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | Financial education package for financial services providers | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.1. Financial education and introduction to financial services: a. assessment of groups, b. development of training material, c. training of trainers, d. training of benficiaries (specific focus on women), e. evaluation of training | VIAMO report | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | G2.3.1 Build capacity of women farmers in financial services and in mobilization of savings to service their businesses | Viamo Report | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | G2.3.1 Build capacity of women farmers in financial services and in mobilization of savings to service their businesses | Database of the project participants | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs |  | 50 saving groups PFMU and 50 FFPO groups stated saving with MFIs | 2026-03-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs |  | 100 acounts opened | 2026-03-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.3. Develop group loan products for cost sharing to acquire envisaged equipment, for example ICS access for targeted households: a. needs/market assessment, b. develop product, c. train staff on product, d. pilot product. | ICS Financial products cutomized with D-SACCO | 2026-01-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.4. Evaluation of mechanism and potentially develop product under 2.3.3: a. develop evaluation criteria for new product | Final report: 7 training sessions organised with 7 D-SACCOs on the FPs customized | 2026-01-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.4. Evaluation of mechanism and potentially develop product under 2.3.3: a. develop evaluation criteria for new product | 1 D-SACCOs supported to cutomize their policies with the developed ICS product | 2026-01-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.1: Financial education and savings mobilization for groups involved in restoration activities and linked with MFIs | 2.3.1.4. Evaluation of mechanism and potentially develop product under 2.3.3: a. develop evaluation criteria for new product | D2.3.1.3b: Evaluation report | 2026-01-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.1. Training MFIs staff: a. scanning portfolio on climate adaption opportunities, b. develop training materials on climate measures/resilient agri-finance/gender, c. train MFI staff, d. evalaute training | D2.3.2.1: Training package for MFis on climate resilient farming/landscape restoration etc(+Attendance sheets) | 2026-01-01 | 2026-03-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.1. Training MFIs staff: a. scanning portfolio on climate adaption opportunities, b. develop training materials on climate measures/resilient agri-finance/gender, c. train MFI staff, d. evalaute training | 4 TREPA/ CORDAID staffTrained on Green Business for climate reselience projects | 2026-01-01 | 2026-03-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.1. Training MFIs staff: a. scanning portfolio on climate adaption opportunities, b. develop training materials on climate measures/resilient agri-finance/gender, c. train MFI staff, d. evalaute training | 7 MoUs signed with all D-SACCOs in Eastern province | 2026-01-01 | 2026-03-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | G2.3.2 Support microfinance institutions (MFIs) in gender-sensitive design of the financial products provided for the agri financial products | 1 Gender Sensitive Products developped+Product documents | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | G2.3.2 Support microfinance institutions (MFIs) in gender-sensitive design of the financial products provided for the agri financial products | Consumption reports from D-SACCOs | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.2. Include indicators in credit assessment: (a. design indicators, b. upgrading A-CAT with climate/forestry indicators, c. train MFI staff on upgraded A-CAT, d. pilot upgraded A-CAT) | 1 Training of TREPA/Cordaid staff on upgraded A-CAT tool for Maize Rice and Beans | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.2. Include indicators in credit assessment: (a. design indicators, b. upgrading A-CAT with climate/forestry indicators, c. train MFI staff on upgraded A-CAT, d. pilot upgraded A-CAT) | Oganise meeting with MINECOFIN for the digitalization of A-CAT tool in D-SACCOs | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.3. Establish monitoring system to verify indicators: (a. mapping of information flows for monitoring (related to other TREPA partners), b. design monitoring system for climate indicators) | 1 Digital tool established (A-CAT) to support the Maize, rice and beans financial products and othe financial products under selected value chains 2.3.4 | 2026-01-01 | 2026-01-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.3. Establish monitoring system to verify indicators: (a. mapping of information flows for monitoring (related to other TREPA partners), b. design monitoring system for climate indicators) | 1 Rollout session of YAPU solution with Duterimbere IMF Plc | 2026-01-01 | 2026-01-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.3. Establish monitoring system to verify indicators: (a. mapping of information flows for monitoring (related to other TREPA partners), b. design monitoring system for climate indicators) | D2.3.2.3: Monitoring system to report on indicators in place | 2026-01-01 | 2026-01-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.4. Test revised products: a. one revised financial product tested. | Guide and coach 2 financial service providers (2 per each D-SACCO) through a testing phase | 2026-04-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.4. Test revised products: a. one revised financial product tested. | Evaluate the new procedures on applicability for farmers and accuracy to measure climate impact through the developed tool | 2026-06-01 | 2026-09-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.4. Test revised products: a. one revised financial product tested. | D2.3.2.4: Testing report available | 2026-04-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.5. Evaluate revised products for mainstreaming: a. develop evaluation criteria for new product | 2 learning products produced on YAPU solusion and A-CAT digital tool after its testing | 2026-02-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.5. Evaluate revised products for mainstreaming: a. develop evaluation criteria for new product | Document at least 1 narrative success story and 1 Video, on the successfulness of the solution | 2026-02-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.2: Promote and upscale agri finance products of MFIs (maize, beans and rice) including water collection, planting of trees, soil erosion mitigation | 2.3.2.5. Evaluate revised products for mainstreaming: a. develop evaluation criteria for new product | D2.3.2.5: Evaluation report available | 2026-06-01 | 2026-09-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.3 Detailed and comprehensive scoping of financial service potential in the respective value chain for detailed product design and development. | G2.3.3 Evaluate effectiveness of financial products in serving the needs of women entrepreneurs | Evaluation report of products under 2.3.2.5 | 2026-07-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.3 Detailed and comprehensive scoping of financial service potential in the respective value chain for detailed product design and development. | 2.3.3.2. Design products and services: a. design (gender sensitive) value chain financial products | Orora mugore financial product is customized and able to serve bee keepersrogress report | 2026-01-01 | 2026-03-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.3 Detailed and comprehensive scoping of financial service potential in the respective value chain for detailed product design and development. | 2.3.3.2. Design products and services: a. design (gender sensitive) value chain financial products | D2.3.3.2: Draft design of key relevant financial products in collaboration with chain actors and MFIs | 2026-01-01 | 2026-03-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.3 Detailed and comprehensive scoping of financial service potential in the respective value chain for detailed product design and development. | 2.3.3.3. Facilitate linkages between chain actors and financial service providers: a. organize linkage sessions, b. faciliate follow-up and access to financial products. | 1 national B2B meeting organised to link TREPA SMES with value chain financers | 2026-05-31 | 2026-10-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.3 Detailed and comprehensive scoping of financial service potential in the respective value chain for detailed product design and development. | 2.3.3.3. Facilitate linkages between chain actors and financial service providers: a. organize linkage sessions, b. faciliate follow-up and access to financial products. | D2.3.3.3: Linkages between key chain actors and financial service providers established. | 2026-05-31 | 2026-10-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.3 Detailed and comprehensive scoping of financial service potential in the respective value chain for detailed product design and development. | 2.3.3.3. Facilitate linkages between chain actors and financial service providers: a. organize linkage sessions, b. faciliate follow-up and access to financial products. | 5000 loan clients in then 3 VCs, 30% are women | 2026-05-31 | 2026-10-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.1. Approval of products and services: (a. faciliate approval process) | D2.3.4.1 Financial products approved for roll out by each MFI and SACCO | 2026-04-01 | 2026-04-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.1. Approval of products and services: (a. faciliate approval process) | Approval document | 2026-04-01 | 2026-04-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.3. Sensitization and financial education of saving groups, already trained on climate impact, to find fund facilities to implement their solutions: a. linkage sessions MFIs, b. facilitation of access to financia VC products c. evaluation of loans/savings at MFI level. | 350 groups/coops linked to (M)FIs | 2026-05-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.3. Sensitization and financial education of saving groups, already trained on climate impact, to find fund facilities to implement their solutions: a. linkage sessions MFIs, b. facilitation of access to financia VC products c. evaluation of loans/savings at MFI level. | 200 groups/coop groups started saving and lending | 2026-05-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.3. Sensitization and financial education of saving groups, already trained on climate impact, to find fund facilities to implement their solutions: a. linkage sessions MFIs, b. facilitation of access to financia VC products c. evaluation of loans/savings at MFI level. | 130,000 credit clients are reached as part of uptake of VC financial products, and loans taken from the SGs. | 2026-06-01 | 2026-09-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.3. Sensitization and financial education of saving groups, already trained on climate impact, to find fund facilities to implement their solutions: a. linkage sessions MFIs, b. facilitation of access to financia VC products c. evaluation of loans/savings at MFI level. | 10M are saved as internal and BANK savings. facilitation of access to finance for VC products | 2026-01-01 | 2026-09-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | Activity 2.3.4: In collaboration with MFI - design and pilot testing of financial products for the respective value chains | 2.3.4.4. Training of staff and clients: a. develop staff training, b. conduct staff traning, c. develop local client marketing campaign. | D2.4.1.2: Client and staffcoaching methodology designed and implemented including climate resilient methods of agriculture and monitoring of the VCs | 2026-01-01 | 2026-05-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.6: Implement the roll out and upscaling plan of financial products developed | 2.3.6.1. Adapt product for mainstreaming at branch and national level | 9 Products are rolled out at Larger scale nd national level with Updated procedural manuals in place at MFIs level | 2026-04-01 | 2026-04-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.6: Implement the roll out and upscaling plan of financial products developed | 2.3.6.1. Adapt product for mainstreaming at branch and national level | D2.3.6.1: Updated procedural manuals in place at MFI level | 2026-04-01 | 2026-04-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.6: Implement the roll out and upscaling plan of financial products developed | 2.3.6.2. Develop each MFI capacity to replicate product | D2.3.6.2: In house training unit per financial service provider to replicate products | 2026-03-01 | 2026-04-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.6: Implement the roll out and upscaling plan of financial products developed | 2.3.6.3. Digitalization of tools and systems to support the financial products: a. assessment of climate fintech options/needs b. pilot with climate fintech option supporting 2.3.2) | Demonstration report | 2026-01-01 | 2026-08-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.6: Implement the roll out and upscaling plan of financial products developed | 2.3.6.3. Digitalization of tools and systems to support the financial products: a. assessment of climate fintech options/needs b. pilot with climate fintech option supporting 2.3.2) | D2.3.6.3: Supportive digital and data management systems in place to properly manage new products | 2026-01-01 | 2026-08-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.1. Business proposals development | D2.3.7.1: Business proposals developed for interested funders. | 2026-01-01 | 2026-10-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.1. Business proposals development | D2.3.7.2: Organize ratings for prospective investees | 2026-01-01 | 2026-10-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.2. Identification of investors and Due diligence: (a. assessment of refinancing options, b. linkage sessions. c. follow-up) | Assessment doc | 2026-01-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.2. Identification of investors and Due diligence: (a. assessment of refinancing options, b. linkage sessions. c. follow-up) | 1 linkage sessions between MFIs and investee | 2026-01-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.2. Identification of investors and Due diligence: (a. assessment of refinancing options, b. linkage sessions. c. follow-up) | D2.3.7.3: Successful conclusion of due diligence process | 2026-01-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.3. Financing contracts | D2.3.7.4: Funding contracts in place for 3 MFis | 2026-07-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.4. Linkage with agri-insurance scheme: a. assessment of insurance options related to TREPA VC, b. linkage sessions, c. follow-up) | D2.3.7.5: MFIs are aware of agri-insurance services available. | 2026-06-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.7: Facilitate impact investors to engage in investment for SMEs in the relevant value chains and connect to insurance companies | 2.3.7.4. Linkage with agri-insurance scheme: a. assessment of insurance options related to TREPA VC, b. linkage sessions, c. follow-up) | Signed MoU with Radiant Yacu & BK Insurance | 2026-06-01 | 2026-11-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.1. Regular collaboration with all program stakeholders and chain actors to tune up all implementation activities: a. participation in TREPA meetings, b. organization of PDCAs, c. meetings wtih project partners and stakeholders. | 2 meertings , 2PDCA. 2 meetings with project partners | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.2. Organize learning events on relevant financial products: a. create factsheet on product development learnings Y2 | 1 learning event with FIs / financial sector+attendence sheets | 2026-05-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.2. Organize learning events on relevant financial products: a. create factsheet on product development learnings Y3 | 1 Factsheet developed for financial product development learnings | 2026-05-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.2. Organize learning events on relevant financial products: a. create factsheet on product development learnings Y4 | D2.3.8.1: Report and action plans from learning events | 2026-05-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.2. Organize learning events on relevant financial products: a. create factsheet on product development learnings Y5 | validated training report of master trainers through a 5-day ToTand certification list | 2026-04-01 | 2026-09-30 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.3. Introduce financial service perspectives in regular program reporting and planning: a. participate in TREPA meetings, b. input on/development of plans, reports, etc. | 6 DPCC Meeting reports | 2026-01-01 | 2026-12-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.4. Organize financial sectors seminars to share lessons learned and solicit interest of other financial sector actors: a. connect with similar projects, b. exchange event with GCF partners, c. case study on tbd topic. | 1 learning event with other projects/Peer Learnings+attendence sheets | 2026-07-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
Cordaid | 2.3.8: Facilitate learning and sharing for replication in the financial sector | 2.3.8.4. Organize financial sectors seminars to share lessons learned and solicit interest of other financial sector actors: a. connect with similar projects, b. exchange event with GCF partners, c. case study on tbd topic. | D2.3.8.3: Sector wide knowledge, understanding and inspiration to finance climate resilient interventions shown through reports and PR materials | 2026-07-01 | 2026-07-31 | Output 2.3 Enhanced financial inclusion and investments in climate resilient value chains products
IUCN | 3.1.1: Organize and facilitate 10 multi-stakeholder workshops to identify and integrate climate resilience metrics into 35 annual district development strategies and performance contracts | 3.1.1.1. Supporting the integration of climate resilience metrics into district development strategies and annual performance contracts through the facilitation of joint planning workshops, using particpatory approach to promote effective and active women particpation. a) Organize meetings at District level to allow IPs present their Annual targets b) Present EE target to Districts c) Support districst develop their strategies and performance contracts with climate resilient metrics | Workshops reports:7 multi-stakeholder workshops held | 2026-02-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.1: Organize and facilitate 10 multi-stakeholder workshops to identify and integrate climate resilience metrics into 35 annual district development strategies and performance contracts | 3.1.1.1. Supporting the integration of climate resilience metrics into district development strategies and annual performance contracts through the facilitation of joint planning workshops, using particpatory approach to promote effective and active women particpation. a) Organize meetings at District level to allow IPs present their Annual targets b) Present EE target to Districts c) Support districst develop their strategies and performance contracts with climate resilient metrics | Final District strategies and performance contracts | 2026-02-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.2: Hold monthly round tables to facilitate the collaboration for adaptation actions between institutions in charge of agriculture and agroforestry | 3.1.2.1. Strengthen collaborative efforts, in particular between institutions in charge of agriculture and agroforestry (i.e. MINAGRI, RAB and RFA) to encourage synergies and avoid overlapping mandates and redundancy in different climate resilience interventions. The first and subsequent monthly round tables can start as soon as the project really kick-off in the Eastern Province, and after the first TREPA inception meetings: last quarter of 2022. | Meeting reports: 4 quarterly meetings per District | 2026-01-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.3: Deliver 5 training sessions at central and district level, to enhance capacities for funding mobilization, planning, and delivery of climate adaptation actions | 3.1.3.1. Training of technical staff (including women staff) including agriculture, livestock and forestry extension agents and planners on climate risks and their implications for cross-sectoral aspects. District level planners will also be better equipped to access funding for adaptation actions from FONERWA and other sources. 3.1.3.1.a) development curricula and training materials on climate risks for the sectors agriculture and forestry, and adaptation solutions with cross-sectoral implications. 3.1.3.1.b) Deliver training | Training materials developed | 2026-07-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.3: Deliver 5 training sessions at central and district level, to enhance capacities for funding mobilization, planning, and delivery of climate adaptation actions | 3.1.3.1. Training of technical staff (including women staff) including agriculture, livestock and forestry extension agents and planners on climate risks and their implications for cross-sectoral aspects. District level planners will also be better equipped to access funding for adaptation actions from FONERWA and other sources. 3.1.3.1.a) development curricula and training materials on climate risks for the sectors agriculture and forestry, and adaptation solutions with cross-sectoral implications. 3.1.3.1.b) Deliver training | Training reports on climate risks for the sectors agriculture and forestry, and adaptation solutions with cross-sectoral implications+ attendance list | 2026-07-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.4: Provide technical assistance for the design and implementation of a cross-sectoral monitoring and reporting mechanism for climate resilient actions | 3.1.4.1. Organisation of knowledge exchange on cross-sectoral monitoring and evaluation. 3.1.4.1 Organize and facilitate cross sectoral annual monitoring and reporting workshops; 3.1.4.2 Joint annual knowledge sharing events (forum) for technicians, decision-makers, planners, policy-makers and landscape restoration managers; 3.1.4.3 Carry out joint 40 (2 times per quarter) field interventions by mixed teams of development agents (e.g. RFA and RAB). | Workshop and event reports | 2026-02-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.4: Provide technical assistance for the design and implementation of a cross-sectoral monitoring and reporting mechanism for climate resilient actions | 3.1.4.1. Organisation of knowledge exchange on cross-sectoral monitoring and evaluation. 3.1.4.1 Organize and facilitate cross sectoral annual monitoring and reporting workshops; 3.1.4.2 Joint annual knowledge sharing events (forum) for technicians, decision-makers, planners, policy-makers and landscape restoration managers; 3.1.4.3 Carry out joint 40 (2 times per quarter) field interventions by mixed teams of development agents (e.g. RFA and RAB). | 8 Field intervention reports | 2026-02-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.4: Provide technical assistance for the design and implementation of a cross-sectoral monitoring and reporting mechanism for climate resilient actions | 3.1.4.1. Organisation of knowledge exchange on cross-sectoral monitoring and evaluation. 3.1.4.1 Organize and facilitate cross sectoral annual monitoring and reporting workshops; 3.1.4.2 Joint annual knowledge sharing events (forum) for technicians, decision-makers, planners, policy-makers and landscape restoration managers; 3.1.4.3 Carry out joint 40 (2 times per quarter) field interventions by mixed teams of development agents (e.g. RFA and RAB). | D3.1.4.1: Annual monitoring and reporting workshop materials | 2026-02-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.4: Provide technical assistance for the design and implementation of a cross-sectoral monitoring and reporting mechanism for climate resilient actions | 3.1.4.1. Organisation of knowledge exchange on cross-sectoral monitoring and evaluation. 3.1.4.1 Organize and facilitate cross sectoral annual monitoring and reporting workshops; 3.1.4.2 Joint annual knowledge sharing events (forum) for technicians, decision-makers, planners, policy-makers and landscape restoration managers; 3.1.4.3 Carry out joint 40 (2 times per quarter) field interventions by mixed teams of development agents (e.g. RFA and RAB). | D3.1.4.2: Knowledge sharing events materials and products | 2026-02-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.4: Provide technical assistance for the design and implementation of a cross-sectoral monitoring and reporting mechanism for climate resilient actions | 3.1.4.1. Organisation of knowledge exchange on cross-sectoral monitoring and evaluation. 3.1.4.1 Organize and facilitate cross sectoral annual monitoring and reporting workshops; 3.1.4.2 Joint annual knowledge sharing events (forum) for technicians, decision-makers, planners, policy-makers and landscape restoration managers; 3.1.4.3 Carry out joint 40 (2 times per quarter) field interventions by mixed teams of development agents (e.g. RFA and RAB). | D3.1.4.3: 40 field intervention reports | 2026-02-01 | 2026-11-30 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.5: Identify and train cross sectoral teams of technicians to become landscape restoration planners and managers in collaboration with communities | Strengthen the capacity of the cross-sectoral teams of technicians (ensure women staff participation) in the East Province for better outreach beyond the project sites, promotion scaling-up of landscape restoration for climate resilience. 3.1.5.1 Identify cross-sectoral teams of technicians to be trained and become landscape restoration planners and managers 3.1.5.2 Organize training materials on planning and implementation of integrated landscape restoration 3.1.5.3 Undertake training of selected teams of technicians on integrated landscape restoration | D3.1.5.1: Report identifying targeted cross sectoral teams | 2026-07-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.5: Identify and train cross sectoral teams of technicians to become landscape restoration planners and managers in collaboration with communities | Strengthen the capacity of the cross-sectoral teams of technicians (ensure women staff participation) in the East Province for better outreach beyond the project sites, promotion scaling-up of landscape restoration for climate resilience. 3.1.5.1 Identify cross-sectoral teams of technicians to be trained and become landscape restoration planners and managers 3.1.5.2 Organize training materials on planning and implementation of integrated landscape restoration 3.1.5.3 Undertake training of selected teams of technicians on integrated landscape restoration | D3.1.5.2: Training materials/manual for integrated landscape restoration+Attendance list | 2026-07-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.7: Train 28 staff in the district authorities and provide technical assistance for the preparation of 7 landscape restoration plans with climate resilience protocols / technical packages at the district level | 3.1.7.1. Assist districts authorities to prepare 7 landscape restoration plans (one per district). This will involve not only training but also provide technical assistance, logistics, acquisition of satellite imagery, GIS system and other surveying means, and guidance in terms of technical analyses as well as economic and financial assessment. Identify gener focal point in each team tasked with the preparation of landscape restorian plans 3.1.7.1. Facilitate logistics and acquisition of satellite imagery, GIS system and other surveying equipment 3.1.7.2. Organize and facilitate training of 28 district staff (4 per district) in operating acquired technical tools and systems 3.1.7.3. Provide guidance in terms of technical analyses as well as economic and financial assessment | D3.1.7.3: Training manual for operating technical tools and systems | 2026-07-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.7: Train 28 staff in the district authorities and provide technical assistance for the preparation of 7 landscape restoration plans with climate resilience protocols / technical packages at the district level | 3.1.7.1. Assist districts authorities to prepare 7 landscape restoration plans (one per district). This will involve not only training but also provide technical assistance, logistics, acquisition of satellite imagery, GIS system and other surveying means, and guidance in terms of technical analyses as well as economic and financial assessment. Identify gener focal point in each team tasked with the preparation of landscape restorian plans 3.1.7.1. Facilitate logistics and acquisition of satellite imagery, GIS system and other surveying equipment 3.1.7.2. Organize and facilitate training of 28 district staff (4 per district) in operating acquired technical tools and systems 3.1.7.3. Provide guidance in terms of technical analyses as well as economic and financial assessment | D3.1.7.4: Training manual/guidelines for economic/financial analysis | 2026-07-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.7: Train 28 staff in the district authorities and provide technical assistance for the preparation of 7 landscape restoration plans with climate resilience protocols / technical packages at the district level | 3.1.7.1. Assist districts authorities to prepare 7 landscape restoration plans (one per district). This will involve not only training but also provide technical assistance, logistics, acquisition of satellite imagery, GIS system and other surveying means, and guidance in terms of technical analyses as well as economic and financial assessment. Identify gener focal point in each team tasked with the preparation of landscape restorian plans 3.1.7.1. Facilitate logistics and acquisition of satellite imagery, GIS system and other surveying equipment 3.1.7.2. Organize and facilitate training of 28 district staff (4 per district) in operating acquired technical tools and systems 3.1.7.3. Provide guidance in terms of technical analyses as well as economic and financial assessment | Landscape Restoration Plans developed | 2026-07-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.1.7: Train 28 staff in the district authorities and provide technical assistance for the preparation of 7 landscape restoration plans with climate resilience protocols / technical packages at the district level | 3.1.7.1. Assist districts authorities to prepare 7 landscape restoration plans (one per district). This will involve not only training but also provide technical assistance, logistics, acquisition of satellite imagery, GIS system and other surveying means, and guidance in terms of technical analyses as well as economic and financial assessment. Identify gener focal point in each team tasked with the preparation of landscape restorian plans 3.1.7.1. Facilitate logistics and acquisition of satellite imagery, GIS system and other surveying equipment 3.1.7.2. Organize and facilitate training of 28 district staff (4 per district) in operating acquired technical tools and systems 3.1.7.3. Provide guidance in terms of technical analyses as well as economic and financial assessment | Training reports on operationalization of Landscape Restoration Plans developed. | 2026-07-01 | 2026-12-31 | Output 3.1 Strengthened gender-responsive climate resilience for coordination cross-sectoral planning & community landscape restoration plans developed
IUCN | 3.2.1: Improve existing knowledge and information systems to ensure effective integration of climate risk related data to support climate informed decision making. | 3.2.1.1. Support the revival and establishment information systems that will enable easy access to knowledge and information by project beneficiaries and stakeholders. Such information systems may include FLR monitoring systems, Climate early warning systems and Knowledge/information exchange systems. 3.2.1.1.a. Conduct an updated gap analysis on the status of knowledge and information systems on climate resilience in the Eastern Province 3.2.1.2.. Determine the needs in terms of technical and financial assistance to update and improve the knowledge and information systems to support climate resilience activities". 3.2.1.3. Improve and where necessary, establish new communication channels between the existing information platforms | D3.2.1.1: Updated gap analysis report on knowledge and information systems | 2026-01-01 | 2026-12-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.1: Improve existing knowledge and information systems to ensure effective integration of climate risk related data to support climate informed decision making. | 3.2.1.1. Support the revival and establishment information systems that will enable easy access to knowledge and information by project beneficiaries and stakeholders. Such information systems may include FLR monitoring systems, Climate early warning systems and Knowledge/information exchange systems. 3.2.1.1.a. Conduct an updated gap analysis on the status of knowledge and information systems on climate resilience in the Eastern Province 3.2.1.2.. Determine the needs in terms of technical and financial assistance to update and improve the knowledge and information systems to support climate resilience activities". 3.2.1.3. Improve and where necessary, establish new communication channels between the existing information platforms | D3.2,1,2: Needs assessment report for technical and financial assistance for improving knowledge and information systems for climate resilience activities | 2026-01-01 | 2026-12-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.1: Improve existing knowledge and information systems to ensure effective integration of climate risk related data to support climate informed decision making. | 3.2.1.1. Support the revival and establishment information systems that will enable easy access to knowledge and information by project beneficiaries and stakeholders. Such information systems may include FLR monitoring systems, Climate early warning systems and Knowledge/information exchange systems. 3.2.1.1.a. Conduct an updated gap analysis on the status of knowledge and information systems on climate resilience in the Eastern Province 3.2.1.2.. Determine the needs in terms of technical and financial assistance to update and improve the knowledge and information systems to support climate resilience activities". 3.2.1.3. Improve and where necessary, establish new communication channels between the existing information platforms | D3.2.1.3: Reports on established platforms and their design, implementation and user guidelines. | 2026-01-01 | 2026-12-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.2: Organize 4 trainings for 18 staff (14 from districts, 1 from RAB, 1 from RFA, 1 from RLMUA and 1 from Meteo-Rwanda) on managing information systems and integrating climate-related aspects | 3.2.2.1.a Identify knowledge needs for managing information systems with integrated climate information (3.2.1.1. Carry out training needs assessment for different information systems) (following completion of activity 3.2.1: i.e. gab and needs assessement for managing knowledge and information systems on climate resilience in the Eastern Province). | D3.2.2.1: Training needs assessment for different types of information system. | 2026-01-01 | 2026-03-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.2: Organize 4 trainings for 18 staff (14 from districts, 1 from RAB, 1 from RFA, 1 from RLMUA and 1 from Meteo-Rwanda) on managing information systems and integrating climate-related aspects | 3.2.2.1.a Identify knowledge needs for managing information systems with integrated climate information (3.2.1.1. Carry out training needs assessment for different information systems) (following completion of activity 3.2.1: i.e. gab and needs assessement for managing knowledge and information systems on climate resilience in the Eastern Province). | Training manuals/guidelines for different information systems | 2026-01-01 | 2026-03-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.2: Organize 4 trainings for 18 staff (14 from districts, 1 from RAB, 1 from RFA, 1 from RLMUA and 1 from Meteo-Rwanda) on managing information systems and integrating climate-related aspects | 3.2.2.1.a Identify knowledge needs for managing information systems with integrated climate information (3.2.1.1. Carry out training needs assessment for different information systems) (following completion of activity 3.2.1: i.e. gab and needs assessement for managing knowledge and information systems on climate resilience in the Eastern Province). | Training reports | 2026-01-01 | 2026-03-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.2: Organize 4 trainings for 18 staff (14 from districts, 1 from RAB, 1 from RFA, 1 from RLMUA and 1 from Meteo-Rwanda) on managing information systems and integrating climate-related aspects | 3.2.2.1.a Identify knowledge needs for managing information systems with integrated climate information (3.2.1.1. Carry out training needs assessment for different information systems) (following completion of activity 3.2.1: i.e. gab and needs assessement for managing knowledge and information systems on climate resilience in the Eastern Province). | Performance review of trained staff and system | 2026-01-01 | 2026-03-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.2: Organize 4 trainings for 18 staff (14 from districts, 1 from RAB, 1 from RFA, 1 from RLMUA and 1 from Meteo-Rwanda) on managing information systems and integrating climate-related aspects | 3.2.2.1.b. Conduct training for technical experts. (3.2.2.2. Organise and facilitate training of staff operating the knowledge and information systems in Eastern Province) ensure women staff participation | D3.2.2.2: Training manuals/guidelines for different information systems | 2026-03-01 | 2026-08-31 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
IUCN | 3.2.2: Organize 4 trainings for 18 staff (14 from districts, 1 from RAB, 1 from RFA, 1 from RLMUA and 1 from Meteo-Rwanda) on managing information systems and integrating climate-related aspects | 3.2.2.3 Follow up performance of trained staff and support maintenance of established or revived information systems | D3.2.2.3: Performance review of trained staff and systems | 2026-02-01 | 2026-11-30 | Output 3.2 Enhanced and coordinated knowledge and information systems for decision and negotiation support
ICRAF | 3.3.1: Integrate climate change aspects in policies and strategies for the seed sector and develop business models to promote climate resilient varieties | 3.3.1.1 Conduct situational assessment on the seed and seedling sector to identify opportunities for promoting climate resilient varieties and development of climate proof business models. | Situation assessment report of seed and seedling sector. | 2026-02-01 | 2026-11-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.1: Integrate climate change aspects in policies and strategies for the seed sector and develop business models to promote climate resilient varieties | 3.3.1.1 Conduct situational assessment on the seed and seedling sector to identify opportunities for promoting climate resilient varieties and development of climate proof business models. | Validation workshop report | 2026-02-01 | 2026-11-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.1: Integrate climate change aspects in policies and strategies for the seed sector and develop business models to promote climate resilient varieties | 3.3.1.2 Assess sector policies and legal framework to identify entry points and integrate climate change aspects to promote climate resilient seed and seedling varieties | Policy and legal framework assessment report. | 2026-02-01 | 2026-11-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.1: Integrate climate change aspects in policies and strategies for the seed sector and develop business models to promote climate resilient varieties | 3.3.1.3 Support the establishment of public-private collaboration platforms based on demand-supply scenarios developed for tree species priority groups, based on which location and size of seed sources to be established can be determined, and quality material promoted through the most appropriate channels of supply, including possible seed marketing associations/networks. | 1 platforms established for climate-resilient priority tree species | 2026-04-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.1: Integrate climate change aspects in policies and strategies for the seed sector and develop business models to promote climate resilient varieties | 3.3.1.3 Support the establishment of public-private collaboration platforms based on demand-supply scenarios developed for tree species priority groups, based on which location and size of seed sources to be established can be determined, and quality material promoted through the most appropriate channels of supply, including possible seed marketing associations/networks. | Report on demand and supply scenarios. | 2026-04-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.1: Integrate climate change aspects in policies and strategies for the seed sector and develop business models to promote climate resilient varieties | 3.3.1.3 Support the establishment of public-private collaboration platforms based on demand-supply scenarios developed for tree species priority groups, based on which location and size of seed sources to be established can be determined, and quality material promoted through the most appropriate channels of supply, including possible seed marketing associations/networks. | Report of identified seed marketing associations/cooperatives. | 2026-04-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.2: Prepare climate informed maps and information portal for habitat suitability for up to 100 climate resilient tree and crop species in Rwanda | 3.3.2.2. Document important patterns of genetic differentiation of selected indigenous tree species to identify climate resilience characteristics and potential for climate adaptation. | Reports available on important patterns of genetic variation and database. | 2026-01-01 | 2026-09-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.2: Prepare climate informed maps and information portal for habitat suitability for up to 100 climate resilient tree and crop species in Rwanda | 3.3.2.3. Develop and introduce a user-friendly decision support system and interactive information portal on "What to Plant Where". | 1 platform for a decision support system (What to plant where), designed and in operation | 2026-02-01 | 2026-11-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.3: Design and establish a national-level breeding programme for up to 25 climate resilient priority species of fruit, food, fodder and timber species | 3.3.3.1 Design a breeding programme for up to 25 priority species, including identification of distribution and deployment zones based on climate information. | Breeding programme design document. | 2026-01-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.3: Design and establish a national-level breeding programme for up to 25 climate resilient priority species of fruit, food, fodder and timber species | 3.3.3.2 Range wide acquisition of priority species from their distribution area, including procurement of superior fruit planting materials and develop germplasm exchange protocols/agreements with regional and international research and development bodies; and range wide collections of plus tree families (from natural stands as well as possible landraces) complementing existing collections | Seed and germaplasm exchange protocal documents. | 2026-01-01 | 2026-10-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.3: Design and establish a national-level breeding programme for up to 25 climate resilient priority species of fruit, food, fodder and timber species | 3.3.3.3 Design and establish mother blocks and BSOs in relevant deployment zones. . | 5 new BSOs/Mother Blocks established. | 2026-01-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.3: Design and establish a national-level breeding programme for up to 25 climate resilient priority species of fruit, food, fodder and timber species | 3.3.3.3 Design and establish mother blocks and BSOs in relevant deployment zones. . | BSOs/Mother Blocks establishment Reports Database on BSOs and MBs | 2026-01-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.3: Design and establish a national-level breeding programme for up to 25 climate resilient priority species of fruit, food, fodder and timber species | 3.3.3.4 Assess, manage and use the mother blocks and BSOs for breeding, acquisition of vegetative propagules and seed procurement. | 14 existing BSOs are maintained and monitored. | 2026-10-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.3: Design and establish a national-level breeding programme for up to 25 climate resilient priority species of fruit, food, fodder and timber species | 3.3.3.4 Assess, manage and use the mother blocks and BSOs for breeding, acquisition of vegetative propagules and seed procurement. | Database on BSOs and MBs | 2026-10-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.4: Conduct 12 trainings for six multi-agency working groups on seed-seedlings and climate adaptation | 3.3.4.1 Conduct training needs assessment for key stakeholders to develop climate resilient seed and seedlings supply systems with the establishment of a tree seed network of local and national stakeholders; and assess the need for introduction of climate proof standards in existing tree germplasm facilities. | Validated Training Need Assessment Report and Gender Analysis Report | 2026-04-01 | 2026-06-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.4: Conduct 12 trainings for six multi-agency working groups on seed-seedlings and climate adaptation | 3.3.4.2 Conduct 12 trainings for 6 multi-agency working groups in relevant methods and relevant technologies in climate resilient tree seed procurement, nursery development and business operation as well as extension of knowledge to target beneficiaries. | Training reports and training manual. | 2026-04-01 | 2026-09-30 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
ICRAF | 3.3.4: Conduct 12 trainings for six multi-agency working groups on seed-seedlings and climate adaptation | 3.3.4.3 Prepare, publish and distribute training, extension and information material in all aspects of the program. | The knowledge products and digital platform are available for extension. | 2026-04-01 | 2026-12-31 | Output 3.3 Seed and seedling supply systems are enhanced to provide diverse climate adapted species and varieties
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.1. Ongoing as part of DeSIRA Project | Published research publications | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.1. Conduct a field research and survey to assess the different agroforestry practices in the Eastern Province | Published research publications | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.2 Assess the productivity characteristics of the identified types of agroforestry systems and develop a framework for evaluation | Published research publications | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.3 Determine the effect of agroforestry trees on biodiversity richness | Published research publications | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.4 Estimate the carbon sequestration potential by different agroforestry systems via dendrometry, tree ring analysis and tree growth studies | Published research publications on Carbon sequestration | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.5 Assess the available knowledge about the effect of trees on water balance in semiarid landscape to provide baseline information | Published research publications | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.6 Assess the role of agroforestry systems for the dynamics of the microclimate | Published research publications | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.1: Produce 6 research publications on the role of agroforestry systems for building climate resilience in semi-arid landscapes | 3.4.1.7 Conduct scenarios to determine trade-offs of agroforestry systems | Published research publications on agroforestry stsyem | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.2: Produce 2 publications on the role of agroforestry systems for food security and building socio-economic resilience of local communities. | 3.4.2.1. Ongoing as part of DeSIRA Project (3.4.2.1. Identify high nutritious (fruits/nuts/fodder) value chains and characterise at least 4 with high potential for building resilience to the local population; 3.4.2.2 Market analysis for selected potential value chains analysed) | Research publications on value chains for building resilience of local populations | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.2: Produce 2 publications on the role of agroforestry systems for food security and building socio-economic resilience of local communities. | 3.4.2.1. Ongoing as part of DeSIRA Project (3.4.2.1. Identify high nutritious (fruits/nuts/fodder) value chains and characterise at least 4 with high potential for building resilience to the local population; 3.4.2.2 Market analysis for selected potential value chains analysed) | Market analysis for the 4 selected value chains | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.5: Conduct 8 capacity building sessions and develop 8 knowledge sharing tools to foster scaling-up of agroforestry systems for climate resilient landscapes and promote sustainable use of biomass energy | 3.4.5.6 Agroforestry monitoring capacity enhanced (Conference and workshops) | 6Training workshops to promote agrofoestry monitoring and build capacity of local team | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated
IUCN | 3.4.5: Conduct 8 capacity building sessions and develop 8 knowledge sharing tools to foster scaling-up of agroforestry systems for climate resilient landscapes and promote sustainable use of biomass energy | 3.4.5.8 Develop 8 of knowledge sharing tools to improve up-take of research for policy and practice | Publication of developed products | 2026-01-01 | 2026-12-31 | Output 3.4 Evidence from best practices generated and disseminated